## Sheet1
task | start date | end date | time (day)
Content management project
Search for suitable vendors advertise on internet, newspaper | 2016-05-01 | 2016-05-07 | 7
define software evaluation process | 2016-05-01 | 2016-05-07 | 7
Prepare request for propose | 2016-05-01 | 2016-05-07 | 7
Send request for further information to vendors | 2016-05-08 | 2016-05-08 | 1
Receive and evaluate further information from vendor | 2016-05-09 | 2016-05-13 | 5
Send request for proposal to vendors | 2016-05-14 | 2016-05-14 | 1
Receive and evaluate proposal from vendor | 2016-05-15 | 2016-05-21 | 7
Vendor demonstrate their solution | 2016-05-22 | 2016-05-25 | 4
Discuss with customer about proposed solutions | 2016-05-26 | 2016-06-01 | 7
Set up enviroment for testing and benchmarking | 2016-06-03 | 2016-06-04 | 2
Test and benchmark | 2016-06-05 | 2016-06-05 | 1
Negotiate with selected vendor | 2016-06-06 | 2016-06-08 | 3
Test, benchmark, negotiate with second selected vendor (optional) | 2016-06-09 | 2016-06-13 | 5
Test, benchmark, negotiate with third selected vendor (optional) | 2016-06-14 | 2016-06-18 | 5
Announce selected vendors | 2016-06-19 | 2016-06-19 | 1
Implement CMS | 2016-06-20 | 2016-08-03 | 45
System training | 2016-08-04 | 2016-08-05 | 2
-1
HRMS project
Detailed discussion | 2016-05-10 | 2016-05-19 | 10
Implementation planning | 2016-05-20 | 2016-05-24 | 5
Design the system | 2016-05-25 | 2016-06-03 | 10
Development the system | 2016-06-04 | 2016-08-02 | 60
Testing the system | 2016-08-03 | 2016-08-12 | 10
Modification request | 2016-08-13 | 2016-08-22 | 10
Create go live plan | 2016-08-23 | 2016-08-24 | 2
Deployment | 2016-08-25 | 2016-08-27 | 3
Training users | 2016-08-28 | 2016-09-03 | 7
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
Formulas:
end date = [start date]+[time (day)]-1
start date = [end date, row above]+1

## Sheet4
task | start | end | time (day)
a | 2016-03-01 | 2016-03-06 | 5
b | 2016-03-03 | 2016-03-13 | 10
c | 2016-03-03 | 2016-03-06 | 3
Formulas:
end = [start]+[time (day)]