## Sheet1
task | start date | end date | time (day)
Content management project
Search for suitable vendors Advertise on internet, newspaper | 2016-04-01 | 2016-04-07 | 7
define software evaluation process | 2016-04-01 | 2016-04-07 | 7
prepare request for propose | 2016-04-01 | 2016-04-07 | 7
send request for further information to vendors | 2016-04-08 | 2016-04-08 | 1
receive and evaluate further information from vendor | 2016-04-09 | 2016-04-13 | 5
send request for proposal to vendors | 2016-04-14 | 2016-04-14 | 1
receive and evaluate proposal from vendor | 2016-04-15 | 2016-04-21 | 7
vendor demonstrate their solution | 2016-04-23 | 2016-04-25 | 3
discuss with customer about proposed solutions | 2016-04-27 | 2016-05-03 | 7
set up enviroment for testing and benchmarking | 2016-05-05 | 2016-05-06 | 2
test and benchmark | 2016-05-08 | 2016-05-08 | 1
negotiate with selected vendor | 2016-05-09 | 2016-05-11 | 3
testing, benchmarking, negotiaton with second selected vendor (optional) | 2016-05-12 | 2016-05-16 | 5
testing, benchmarking, negotiaton with third selected vendor (optional) | 2016-05-17 | 2016-05-21 | 5
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
Formulas:
end date = [start date]+[time (day)]-1

## Sheet4
task | start | end | time (day)
a | 2016-03-01 | 2016-03-06 | 5
b | 2016-03-03 | 2016-03-13 | 10
c | 2016-03-03 | 2016-03-06 | 3
Formulas:
end = [start]+[time (day)]