## Sheet1
task | start date | end date | time (day)
Set up hardware
Find suitable hardware | 2016-05-01 | 2016-05-14 | 14
Set up electricity system | 2016-05-15 | 2016-05-19 | 5
Set up hardware | 2016-05-20 | 2016-05-26 | 7
Set up network(wifi, internet, LAN) | 2016-05-20 | 2016-05-26 | 7
Test hardware system | 2016-05-27 | 2016-05-31 | 5
Content management project
Search for suitable vendors advertise on internet, newspaper | 2016-06-01 | 2016-06-07 | 7
define software evaluation process | 2016-06-01 | 2016-06-07 | 7
Prepare request for propose | 2016-06-01 | 2016-06-07 | 7
Send request for further information to vendors | 2016-06-08 | 2016-06-08 | 1
Receive and evaluate further information from vendor | 2016-06-09 | 2016-06-13 | 5
Send request for proposal to vendors | 2016-06-14 | 2016-06-14 | 1
Receive and evaluate proposal from vendor | 2016-06-15 | 2016-06-21 | 7
Vendor demonstrate their solution | 2016-06-22 | 2016-06-25 | 4
Discuss with customer about proposed solutions | 2016-06-26 | 2016-07-02 | 7
Set up enviroment for testing and benchmarking | 2016-07-03 | 2016-07-04 | 2
Test and benchmark | 2016-07-05 | 2016-07-05 | 1
Negotiate with selected vendor | 2016-07-06 | 2016-07-08 | 3
Test, benchmark, negotiate with second selected vendor (optional) | 2016-07-09 | 2016-07-13 | 5
Test, benchmark, negotiate with third selected vendor (optional) | 2016-07-14 | 2016-07-18 | 5
Announce selected vendors | 2016-07-19 | 2016-07-19 | 1
Implement CMS | 2016-07-20 | 2016-09-02 | 45
System training | 2016-09-04 | 2016-09-05 | 2
HRMS system
Detailed discussion | 2016-06-10 | 2016-06-19 | 10
Implementation planning | 2016-06-20 | 2016-06-24 | 5
Design the system | 2016-06-25 | 2016-07-04 | 10
Develop the system | 2016-07-05 | 2016-09-02 | 60
Test the system | 2016-09-03 | 2016-09-12 | 10
Modify request | 2016-09-13 | 2016-09-22 | 10
Create go live plan | 2016-09-23 | 2016-09-24 | 2
Deployment | 2016-09-25 | 2016-09-27 | 3
Training users | 2016-09-28 | 2016-10-04 | 7
CRM system
Assess and make recommendation to current hardware | 2016-06-10 | 2016-06-19 | 10
Design user interface | 2016-06-10 | 2016-06-19 | 10
Define usecases, flowcharts, statecharts | 2016-06-10 | 2016-06-23 | 14
Define test cases | 2016-06-10 | 2016-06-23 | 14
Develop system | 2016-06-24 | 2016-09-21 | 90
Test and fix bugs | 2016-09-22 | 2016-09-28 | 7
Evaluate system | 2016-09-29 | 2016-10-01 | 3
Deploy system | 2016-10-02 | 2016-10-04 | 3
System training | 2016-10-05 | 2016-10-07 | 3
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
Formulas:
end date = [start date]+[time (day)]-1
start date = [end date, row above]+1

## Sheet4
task | start | end | time (day)
a | 2016-03-01 | 2016-03-06 | 5
b | 2016-03-03 | 2016-03-13 | 10
c | 2016-03-03 | 2016-03-06 | 3
Formulas:
end = [start]+[time (day)]