## Sheet1
task | start date | end date | time (day)
Content management project
Search for suitable vendors Advertise on internet, newspaper | 2016-05-01 | 2016-05-07 | 7
define software evaluation process | 2016-05-01 | 2016-05-07 | 7
prepare request for propose | 2016-05-01 | 2016-05-07 | 7
send request for further information to vendors | 2016-05-08 | 2016-05-08 | 1
receive and evaluate further information from vendor | 2016-05-09 | 2016-05-13 | 5
send request for proposal to vendors | 2016-05-14 | 2016-05-14 | 1
receive and evaluate proposal from vendor | 2016-05-15 | 2016-05-21 | 7
vendor demonstrate their solution | 2016-05-22 | 2016-05-25 | 4
discuss with customer about proposed solutions | 2016-05-26 | 2016-06-01 | 7
set up enviroment for testing and benchmarking | 2016-06-03 | 2016-06-04 | 2
test and benchmark | 2016-06-05 | 2016-06-05 | 1
negotiate with selected vendor | 2016-06-06 | 2016-06-08 | 3
testing, benchmarking, negotiaton with second selected vendor (optional) | 2016-06-09 | 2016-06-13 | 5
testing, benchmarking, negotiaton with third selected vendor (optional) | 2016-06-14 | 2016-06-18 | 5
implement CMS | 2016-06-19 | 2016-08-02 | 45
-1
-1
HRMS project |  | -1
vender selection | 2016-05-05 | 2016-05-11 | 7
detailed discussion | 2016-05-11 | 2016-05-13 | 3
implementation planning | 2016-05-13 | 2016-05-17 | 5
design the system | 2016-05-17 | 2016-05-26 | 10
development the system | 2016-05-26 | 2016-07-24 | 60
testing the system | 2016-07-24 | 2016-08-02 | 10
modification request | 2016-08-02 | 2016-08-11 | 10
create go live plan | 2016-08-11 | 2016-08-12 | 2
deployment | 2016-08-12 | 2016-08-14 | 3
training users | 2016-08-14 | 2016-08-16 | 3
ongoing support | 2016-08-16 | 2016-11-13 | 90
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
Formulas:
end date = [start date]+[time (day)]-1
start date = [end date, row above]

## Sheet4
task | start | end | time (day)
a | 2016-03-01 | 2016-03-06 | 5
b | 2016-03-03 | 2016-03-13 | 10
c | 2016-03-03 | 2016-03-06 | 3
Formulas:
end = [start]+[time (day)]